# Uepaki — Professional Onboarding Playbook

From “yes, I’m interested” to an activated professional

9 October 2026 · Internal operating playbook · Not public copy

# Purpose and principle

Onboarding exists to turn an interested professional into an activated professional: approved, with a complete profile, at least one live listing, and payout details complete. It is a service the team delivers, not a form the professional is left to fill in.

Principle: remove every avoidable step and surprise before the professional meets it. The biggest losses in a marketplace funnel usually come from friction nobody warned the seller about. In Uepaki’s case the evidence names several such points (§2).

Every checklist item carries a verification status. Items marked CONFIRM depend on product behaviour the library has traced only in code, or not at all. The onboarding lead must confirm them against the live seller flow, web and app, before Wave 0, and update this playbook.

# 1. Roles

| Role | Responsibility |
| --- | --- |
| Onboarding lead | Owns every professional from “interested” to “activated”: booking calls, the checklists, chasing stuck stages |
| Founder | Policy, terms, fee and tax-adjacent questions; founding welcome; escalations |
| Engineering contact | Defects in registration, KYC, listing and payout flows |
| Legal team (headed by Mr. Satish Kumar Mittal) | Serious cases and appeals (Q-REVIEWER), not described as independent |

# 2. Known friction to fix or prepare for before Wave 0

These are drawn from the library’s evidence records. Each is either an engineering item or a script item; none is a reason to make promises.

| # | Friction | Evidence | Effect on onboarding | Action |
| --- | --- | --- | --- | --- |
| F1 | Registration requires an online payment of ₹1 + GST through Razorpay, even on the “free” path | EV-01 (a) | Payment-step drop-off; confusion if the professional was told “free” | Disclose in advance (SUB-01). Script it. Watch for payment failures |
| F2 | The web and app paths differ: the app charges nothing and creates no subscription row | SUB-06 | Inconsistent experience; possible support cases | Recommend one path (web) for Wave 0–1 until aligned. CONFIRM |
| F3 | Sign-up redirects to the Refer & Earn page, although the referral launch is deferred | Launch-library status note | Confusing; implies referral rewards | Fix before Wave 0 (engineering). Until fixed, warn the professional |
| F4 | Orders are blocked for sellers without a verified, active GSTIN (code check at order placement) | EV-01 (c) | A professional can be activated yet unable to receive orders | Pre-registration readiness check (§3). Do not give tax advice. Escalate policy to the founder and CA (CA-KYC, Q-KYC) |
| F5 | GST-at-listing for goods: the rule exists, but no caller was found | EV-01 (b) | Uncertain whether unregistered sellers can list goods | CONFIRM |
| F6 | Product creation requires KYC, an approved store and account standing | EV-01 (b) | Approval step must be complete before listing | Track store approval as its own step |
| F7 | create_listing is currently subscription-gated in code, contrary to the free-core policy | Code handoff row 1 (U-3) | A free seller might be refused a listing type | CONFIRM which listing path an ordinary seller uses; engineering alignment |
| F8 | Withdrawing earnings is currently premium in code (U-1 open) | Code handoff row 13 | A free seller may be unable to withdraw order earnings | Founder decision U-1; do not describe payouts until resolved |
| F9 | Two definitions of “active subscription” (a 90-day free row passes some gates, fails others) | EV-01 (d) | Inconsistent feature access in the first 90 days | Engineering; script “if a feature is refused, tell us” |
| F10 | Product listing is limited to three categories (Fashion & Lifestyle, Space & Design, Digital & Visual Arts); services are open to all categories with KYC | EV-01 (b); EV-02 | Beauty, Lens and Content professionals list services, not products | Category-specific first-listing guidance (§7) |
| F11 | Which service and booking features are on at launch | EV-09 | Service professionals’ first listing may depend on it | CONFIRM; do not promise booking features |
| F12 | Seller terms are an internal draft, not yet approved for seller acceptance | Seller Policy v1.4 | Professionals may be asked to accept terms not yet final | Founder/legal: no live acceptance until approved; use the interim information note before then |

# 3. Pre-registration readiness check (before sending the registration link)

Ask these on the call, or in writing, once a professional says yes. The aim is to prevent a dead end later, not to screen anyone out: Uepaki is open to all sellers (E10).

| # | Question | Why | If the answer is a problem |
| --- | --- | --- | --- |
| R1 | Which category and what will you list first: products, services or designs? | Products are open only in three categories (F10) | Agree a realistic first listing (§7) |
| R2 | Do you have an active GSTIN for the business? | Orders require a verified, active GSTIN in the current code (F4) | Do not advise on tax. Note it; escalate to the founder. Tell the professional honestly that GST status affects whether orders can be received, and that we’ll confirm the current position in writing |
| R3 | Do you have a PAN and a bank account in the business’s or your name for payouts? | KYC and payouts (exact checks: Q-KYC open) | Note it; CONFIRM requirements |
| R4 | Who will manage the account: you or a team member? | Contact and permissions (team invites are a paid feature) | Note it |
| R5 | Are you comfortable paying ₹1 + GST online to register? | F1 | Explain why the charge exists only from approved wording; otherwise “it’s the registration charge” |
| R6 | Do you have 6 or more good images of your own work, and short descriptions/prices for 1–3 items or services? | Profile and first listing | Offer to help select from their site or Instagram, with permission |
| R7 | Consents: may we mention you to peers once you’ve joined? Social promotion (founding)? WhatsApp updates? | Who-has-joined framework; AiSensy flow | Record each separately; “no” is fine |

# 4. Checklists

## 4.1 Professional onboarding checklist (owner: onboarding lead)

- ☐ Interest recorded (stage 5) with the date and the source message ID

- ☐ Information note sent (interim note until the seller terms are approved)

- ☐ Readiness check R1–R7 done; issues logged

- ☐ Registration link sent (web path recommended for now)

- ☐ Registration started (account visible in admin)

- ☐ Registration completed (₹1 + GST paid; confirmation received)

- ☐ KYC submitted

- ☐ KYC approved and store approved

- ☐ Profile completed (§4.3)

- ☐ Portfolio uploaded (§4.4)

- ☐ First listing live (§4.5)

- ☐ Payout details complete (§4.6)

- ☐ Activation confirmed (§4.7) and recorded in the tracker

- ☐ Consents recorded (naming, promotion, WhatsApp)

- ☐ Founding qualification checked (once FP-QUAL is decided) and founding welcome sent

- ☐ Seven-day post-activation check-in done

## 4.2 KYC checklist

The exact mandatory checks before listing or payout are OPEN (Q-KYC, CA-KYC). The code refers to a “three-pillar KYC” without the pillars being recorded in the library. Confirm every line against the live flow.

| Item | Status |
| --- | --- |
| Legal name and business name match across the account | CONFIRM |
| PAN | CONFIRM — likely; CA-KYC lists PAN/GST checks as the open question |
| GSTIN (verified and active) | Required for orders in the current code (EV-01 c). Listing rule unconfirmed (F5) |
| Bank account for payouts (name match) | CONFIRM |
| Address / city | CONFIRM |
| Category selection | Required (category drives features) |
| Store approval (admin) | Required for product creation (EV-01 b). Approval turnaround: measure it |
| Policy acceptance | Not live until the Seller Policy is approved (F12) |

## 4.3 Profile completion checklist

- ☐ Professional or studio name as used publicly; correct spelling

- ☐ City and service area (for services)

- ☐ Category and subcategory chosen correctly

- ☐ Profile photo or logo (their own)

- ☐ Short professional description in their own words (we can draft; they approve)

- ☐ What they offer: products, services, designs, commissions

- ☐ Pricing approach visible on at least one listing

- ☐ Policies relevant to them acknowledged (made-to-order, cancellations), from approved policy text only

- ☐ Contact preferences inside Uepaki (off-platform rules: SP-4a open — do not advise beyond approved text)

- ☐ Consent-to-be-named recorded (yes/no)

## 4.4 Portfolio checklist

- ☐ At least 6 images of their own work (recommendation; set the final minimum with product)

- ☐ Images they own or have the right to use; no other photographer’s work without credit and permission

- ☐ For photographers and filmmakers: client consent for identifiable people, as their own practice requires (Uepaki does not verify this; remind them)

- ☐ No AI-generated or edited-to-mislead images presented as real work (E3 spirit)

- ☐ Captions that say what the work is (material, technique, project, year)

- ☐ Variety: 2–3 types of work they want to be known for

- ☐ Image quality: in focus, good light, no heavy watermarks over the work

## 4.5 First listing / service checklist

- ☐ Listing type allowed for their category (F10)

- ☐ Clear title in plain words (what it is, for whom)

- ☐ 3 or more images of this specific item or service

- ☐ Price (or a “starting from” price for services, if supported — CONFIRM)

- ☐ For products: size or dimensions, materials, made-to-order or ready stock (made-to-order is online-only per C039), dispatch readiness. The 48-hour dispatch deadline is a policy point; its consequence is OPEN (Q-DISPATCH)

- ☐ For services: what’s included, duration, location/travel, booking lead time. Booking features depend on launch configuration and paid plan (F11; 23 C3)

- ☐ Cancellation and returns from approved policy text only

- ☐ Published and visible to customers (check from a customer view)

## 4.6 Payout readiness

- ☐ Bank details complete and verified (CONFIRM process)

- ☐ The professional understands, from approved terms only, when and how payouts happen. Do not describe payout timing or holds (Q-HOLD open)

- ☐ U-1 resolved (can free sellers withdraw?) before describing withdrawals

## 4.7 Activation checklist (the definition of “activated”)

All must be true:

- ☐ Registration completed

- ☐ KYC approved and store approved

- ☐ Profile completed (§4.3)

- ☐ At least one live listing (§4.5)

- ☐ Payout details complete (§4.6)

- ☐ No open account-standing issue (not suspended, frozen or banned)

Recorded with the date. Activation is signed off weekly by the founder. The same checklist is in UEPAKI_SELLER_ACTIVATION_CHECKLIST.xlsx, where completion and the activated flag are calculated automatically.

# 5. The 48/72-hour onboarding sequence

The clock starts when the professional says yes (stage 5, Interested). The goal is a registration completed within 48 hours and a first listing live within 72 hours of approval. These are targets to test, not promises to the professional.

| When | Action | Channel | Owner |
| --- | --- | --- | --- |
| T+0 (same business day) | Thank them. Send the information note. Offer two time slots for a 15-minute set-up call. Ask the readiness questions R1–R7 if there’s no call | The channel they replied on | Onboarding lead |
| T+0 to T+24h | Set-up call. Readiness check; walk through registration together; agree the first listing; collect consents | Call / video | Onboarding lead |
| T+24h | If registration is not started: one short, helpful nudge, with the link and the step they stopped at | Same channel (WhatsApp only if they invited it) | Onboarding lead |
| T+48h | If registration is started but not completed: offer help with the payment or form step (AiSensy template T03 if opted in) | As above | Onboarding lead |
| T+48h | If still not started: one final note (“I’ll leave it with you; reply any time”) and move to “Stalled — interested” | As above | Onboarding lead |
| Approval (A) | Confirm approval the same day. Book or continue profile set-up | Email / WhatsApp if opted in | Onboarding lead |
| A+24h | Profile draft prepared together (from their own material) and sent for their approval | Email | Onboarding lead |
| A+48h | First listing drafted together and published once approved by them | Call / email | Onboarding lead |
| A+72h | If not yet live: a short call to unblock (template T04 if opted in). Escalate any product defect the same day | Call | Onboarding lead |
| Activation | Activation recorded; founding welcome if qualified; consents re-confirmed | Email | Founder / lead |
| Activation + 7 days | Check-in: anything confusing? Feedback survey | Email | Onboarding lead |

Rules.

- No more than one nudge per 24 hours.

- Never nudge someone who said “later”: diarise the date they gave.

- WhatsApp only where the professional invited it.

- AiSensy templates only with a recorded opt-in.

# 6. Support escalation

| Level | Handles | Response target (internal test target) |
| --- | --- | --- |
| L1 Onboarding lead | How-to questions, registration help, profile and listing help | Same business day |
| L2 Founder | Terms, fees, plans, GST/KYC policy questions, founding programme, complaints, anything not in approved text | Within 1 business day |
| L3 Engineering | Payment failures, KYC/approval errors, listing errors, payout setup errors | Logged within 1 business day; the professional updated every 48 hours until fixed |
| Legal team (Q-REVIEWER) | Serious cases, disputes, appeals | As the policy sets out (appeal periods OPEN) |

Escalation triggers:

- Payment failure.

- KYC rejection.

- Store approval taking more than 3 business days (initial test threshold).

- Any GST question.

- Any request to communicate outside Uepaki (SP-4a).

- Any data or IP question.

- Any complaint.

- Anyone saying they were told it was free.

Log every escalation with Prospect/seller ID, stage, issue, owner, opened and closed dates, and outcome. Recurring issues go to the weekly activation review.

# 7. Category-specific first listings

| Category | Realistic first listing | Notes |
| --- | --- | --- |
| Fashion & Lifestyle | 3–10 products that already sell on their own store | Self-ship disabled (E12); shipping through Uepaki’s logistics arrangement |
| Space & Design | Makers: 3–5 pieces. Studios: one service/project listing | CONFIRM that large items are supported by logistics before listing them |
| Digital & Visual Arts | One product (print, stationery) or one commission/service | Products allowed in this category (F10) |
| Beauty & Makeup | One service (for example, a bridal package) | No product listing in this category (F10). Bookings are a paid-plan feature (23 C3); launch configuration (EV-09) |
| Lens & Motion | One service (for example, wedding photography coverage) | As above |
| Content & Media | One service (for example, hosting a sangeet, a content package) | As above |

# 8. What onboarding staff must never say

- “It’s free.” (It is ₹1 + GST.)

- “You’ll get orders/bookings/clients soon.”

- “Complete your profile to rank higher.” (No ranking explanations; B4/EV-08.)

- Any commission, plan price, payout timing or tax advice.

- “Your GST doesn’t matter.” Or any tax advice at all.

- “Everyone else in your category has already joined.”

- Anything about referral rewards, Fame Circle or Brand Ambassador.